# DOC-004 – KPI Dictionary

Document ID: DOC-004
Project: Construction Analytics Solution
Version: 0.1
Status: Draft
Author: Mark Vecchione
Last Updated: July 2026

## 1. Purpose

The KPI Dictionary defines the Key Performance Indicators (KPIs) used throughout the Construction Analytics Solution.

Its purpose is to establish a consistent business definition for each KPI, ensure calculations are interpreted consistently across dashboards, and provide a common language for executives, project managers, operations, finance, and analysts.

Detailed calculation logic, source tables, SQL implementation, and technical metadata are maintained separately within the KPI Catalog (DOC-008).

## 2. KPI Philosophy

The Construction Analytics Solution is designed to answer one fundamental business question:

"How are we doing today?"

Rather than focusing solely on historical accounting information, the solution emphasizes operational performance and leading indicators that allow management to identify issues while corrective action is still possible.

KPIs are intended to support decision-making rather than simply report historical results.

## 3. KPI Classification

KPIs are organized into three categories.

### 3.1 Outcome KPIs

Outcome KPIs measure the financial results of completed work and indicate whether business objectives have been achieved.

Examples include:

- Gross Margin %

- Gross Profit

- Revenue

These are considered lagging indicators.

### 3.2 Performance KPIs

Performance KPIs measure how effectively work is currently being executed.

Examples include:

- Labor Productivity

- Production Rate

- Equipment Utilization

- Material Quantity Variance

These are considered leading indicators because they provide visibility into project performance before financial results are finalized.

### 3.3 Predictive KPIs

Predictive KPIs estimate future project performance based on current operational information.

Examples include:

- Project Health (Future)

- Forecast Margin (Future)

- Labor Progress Index (Working Name)

These KPIs are intended to identify potential issues before they affect project profitability.

## 4. KPI Governance

Each KPI shall have:

- A single business definition

- A documented business purpose

- A clearly identified business owner

- One approved calculation methodology

- One primary source of truth

- Traceability to business requirements and dashboards

Business calculations will be implemented once within the SQL analytics layer and consumed consistently by all reporting tools.

## 5. Core KPI Catalog

The following KPIs have been identified for Version 1 of the Construction Analytics Solution.

| KPI ID | KPI | Category | Indicator Type | Status |
| --- | --- | --- | --- | --- |
| KPI-001 | Gross Margin % | Financial | Lagging | Approved |
| KPI-002 | Budget Variance | Financial | Leading | Approved |
| KPI-003 | Labor Progress (Working Name) | Labor | Leading | Draft |
| KPI-004 | Labor Productivity | Labor | Leading | Approved |
| KPI-005 | Production Rate | Production | Leading | Approved |
| KPI-006 | Production Variance | Production | Leading | Draft |
| KPI-007 | Material Quantity Variance | Materials | Leading | Approved |
| KPI-008 | Equipment Utilization | Equipment | Leading | Approved |
| KPI-009 | Project Progress | Project | Leading | Draft |
| KPI-010 | Forecast Margin | Project | Predictive | Future |
| KPI-011 | Project Health | Project | Predictive | Future |

## 6. KPI Definitions

Each KPI within the Construction Analytics Solution shall be documented using the following format:

- KPI ID

- KPI Name

- Business Capability

- Business Question

- Purpose

- Business Importance

- Indicator Type

  - Leading

  - Lagging

  - Predictive

- Primary Users

- Supporting Metrics

- Related Dashboards

- Notes

## 7. KPI Lifecycle

KPIs evolve throughout the project lifecycle.

Draft

The KPI has been identified but requires further definition.

Approved

The KPI definition has been finalized and approved for implementation.

Future

The KPI has been identified for future releases but will not be implemented in Version 1.

## 8. Relationship to Other Documentation

The KPI Dictionary is part of the overall solution governance process.

Business Discovery

↓

Business Questions

↓

KPI Dictionary

↓

KPI Catalog

↓

SQL Analytics Layer

↓

Power BI / Tableau

This document defines what each KPI means.

The KPI Catalog defines how each KPI is calculated.

## 9. Future Enhancements

Future versions of the solution may include additional KPIs, including:

- Forecast Cost at Completion

- Earned Value Metrics

- Schedule Performance

- Crew Performance Index

- Equipment Reliability

- Customer Satisfaction

- Safety Performance